MEDICURE DIGITAL HEALTH PLATFORM

Project Cost Analysis Report

Team: 2 Developers  |  Duration: 3 Months  |  Context: Bangladesh (BDT)

1. Project Overview

| Project Name | Medicure – Digital Health Platform |
| --- | --- |
| Team Size | 2 Developers (1 Senior, 1 Junior) |
| Project Duration | 3 Months (April 2026 – June 2026) |
| Technology Stack | PHP, MySQL, HTML/CSS/JavaScript, XAMPP |
| Project Context | Academic + Real-world digital health use-case, Bangladesh |

2. Team & Rate Structure

The project is executed by a two-person development team over a period of three months. Monthly salary rates reflect mid-market rates for software developers in Dhaka, Bangladesh.

| Role | Skill Level | Monthly Salary (BDT) | 3-Month Cost (BDT) | Working Hours/Month |
| --- | --- | --- | --- | --- |
| Developer 1 | Senior / Full-Stack Lead | ৳ 60,000 | ৳ 1,80,000 | 176 hrs |
| Developer 2 | Junior / Frontend & QA | ৳ 30,000 | ৳ 90,000 | 176 hrs |
| TOTAL | — | ৳ 90,000 / month | ৳ 2,70,000 | 352 hrs / month |

3. WBS-Based Cost Allocation (Direct Labor)

Project work is decomposed into five phases following a Phase-Based WBS. Hours are distributed across developers and phases to reflect realistic effort.

| Phase | WBS Task | Dev 1 (hrs) | Dev 2 (hrs) | Total (hrs) | Rate (BDT/hr) | Labor Cost (BDT) |
| --- | --- | --- | --- | --- | --- | --- |
| Phase 1: Initiation | 1.1 Requirements & Scope Analysis | 12 | 8 | 20 | 341 | ৳ 6,818 |
| Phase 1: Initiation | 1.2 Feasibility Study | 8 | 4 | 12 | 341 | ৳ 4,091 |
| Phase 1: Initiation | 1.3 Project Charter & Planning | 8 | 4 | 12 | 341 | ৳ 4,091 |
| Phase 2: Design | 2.1 UI/UX Wireframes & Mockups | 12 | 20 | 32 | 341 | ৳10,909 |
| Phase 2: Design | 2.2 Database Schema Design | 16 | 8 | 24 | 341 | ৳ 8,182 |
| Phase 2: Design | 2.3 System Architecture Planning | 12 | 4 | 16 | 341 | ৳ 5,455 |
| Phase 3: Development | 3.1 Backend (PHP, Auth, DB, APIs) | 96 | 40 | 136 | 341 | ৳46,364 |
| Phase 3: Development | 3.2 Frontend (HTML/CSS/JS, Dashboard) | 32 | 80 | 112 | 341 | ৳38,182 |
| Phase 3: Development | 3.3 Symptom Checker AI Module | 40 | 16 | 56 | 341 | ৳19,091 |
| Phase 3: Development | 3.4 Pharmacy & Medicines Module | 32 | 24 | 56 | 341 | ৳19,091 |
| Phase 3: Development | 3.5 Family Health Management Module | 24 | 16 | 40 | 341 | ৳13,636 |
| Phase 3: Development | 3.6 Reports & Health Calculators | 20 | 20 | 40 | 341 | ৳13,636 |
| Phase 4: Testing | 4.1 Unit & Integration Testing | 12 | 24 | 36 | 341 | ৳12,273 |
| Phase 4: Testing | 4.2 User Acceptance Testing (UAT) | 8 | 16 | 24 | 341 | ৳ 8,182 |
| Phase 4: Testing | 4.3 Bug Fixing & QA | 16 | 16 | 32 | 341 | ৳10,909 |
| Phase 5: Deployment | 5.1 Server Setup & Deployment | 16 | 8 | 24 | 341 | ৳ 8,182 |
| Phase 5: Deployment | 5.2 Documentation & User Manual | 8 | 16 | 24 | 341 | ৳ 8,182 |
| Phase 5: Deployment | 5.3 Final Handover & Training | 4 | 8 | 12 | 341 | ৳ 4,091 |
| TOTAL | — | 376 | 332 | 708 | — | ৳2,41,364 |

* Blended hourly rate = (৳60,000 + ৳30,000) ÷ (2 × 132 working hrs/month*) ≈ ৳341/hr  |  *Assumes 22 working days × 6 hrs billable/day

4. Direct & Indirect Costs Breakdown

4.1 Direct Costs

| Cost Category | Item | Qty | Unit Cost (BDT) | Total (BDT) |
| --- | --- | --- | --- | --- |
| Labor – Senior Developer | Full-stack development (3 months) | 1 | ৳60,000/mo | ৳1,80,000 |
| Labor – Junior Developer | Frontend & QA (3 months) | 1 | ৳30,000/mo | ৳ 90,000 |
| Software & Tools | VS Code, Git, XAMPP, MySQL Workbench | 1 | Free/OSS | ৳ 0 |
| Software & Tools | Adobe XD / Figma (Pro plan, 3 months) | 1 | ৳2,500/mo | ৳ 7,500 |
| Software & Tools | GitHub Copilot subscription (3 months) | 2 | ৳1,200/mo | ৳ 7,200 |
| Hardware / Equipment | Laptop usage allocation (depreciation) | 2 | ৳2,000/mo | ৳ 12,000 |
| Testing | Device testing (Android/iOS simulators) | 1 | Lump sum | ৳ 3,000 |
|  | DIRECT COST SUBTOTAL |  |  | ৳2,99,700 |

4.2 Indirect Costs

| Cost Category | Item | Monthly (BDT) | Total 3 Months (BDT) |
| --- | --- | --- | --- |
| Infrastructure | Shared hosting / local server electricity | ৳ 1,000 | ৳ 3,000 |
| Infrastructure | Internet (broadband 2 devs) | ৳ 1,400 | ৳ 4,200 |
| Administrative | Project management / meeting overhead | ৳ 800 | ৳ 2,400 |
| Communication | Slack, email, cloud storage (Google Drive) | ৳ 500 | ৳ 1,500 |
| Training | Online courses / documentation references | ৳ 500 | ৳ 1,500 |
|  | INDIRECT COST SUBTOTAL |  | ৳ 12,600 |

5. Opportunity & Risk-Related Costs

| Cost Type | Description | Estimated Amount (BDT) |
| --- | --- | --- |
| Opportunity Cost | Revenue/freelance income forgone by 2 devs for 3 months (~40% of salary) | ৳ 1,08,000 |
| Risk Contingency | 10% of total project cost (Direct + Indirect) reserved for scope creep | ৳ 31,230 |
| Risk – Technical | Unexpected bug resolution, library upgrades, server failures | ৳ 10,000 |
| Risk – Scope Creep | Additional feature requests beyond original WBS | ৳ 15,000 |
|  | RISK & OPPORTUNITY SUBTOTAL | ৳ 56,230 |

6. Cost Baseline & Total Project Budget

The Cost Baseline is the approved planned budget (excluding management reserves). It serves as the reference for Earned Value Analysis throughout the project lifecycle.

| Budget Component | Amount (BDT) | Notes |
| --- | --- | --- |
| A. Direct Costs (Labor + Tools + Hardware) | ৳ 2,99,700 | Primary project expenditure |
| B. Indirect Costs (Overhead) | ৳ 12,600 | Operational support costs |
| ── COST BASELINE (A + B) | ৳ 3,12,300 | Approved performance reference |
| C. Contingency Reserve (10%) | ৳ 31,230 | Known risks buffer |
| ── CONTROL ACCOUNT BUDGET (A+B+C) | ৳ 3,43,530 | Project budget with contingency |
| D. Management Reserve (5%) | ৳ 15,627 | Unknown unknowns – separate |
| ══ TOTAL PROJECT BUDGET (A+B+C+D) | ৳ 3,59,157 | Full authorization level |

7. Time-Phased Budget (Monthly Cost Baseline)

Costs are distributed across three months based on planned work intensity per phase. Month 1 covers initiation and design; Month 2 is the heaviest development sprint; Month 3 covers testing, deployment, and wrap-up.

| Cost Item | Month 1 – April 2026 (BDT) | Month 2 – May 2026 (BDT) | Month 3 – June 2026 (BDT) | Total (BDT) |
| --- | --- | --- | --- | --- |
| Senior Developer Labor | ৳ 60,000 | ৳ 60,000 | ৳ 60,000 | ৳ 1,80,000 |
| Junior Developer Labor | ৳ 30,000 | ৳ 30,000 | ৳ 30,000 | ৳ 90,000 |
| Software Tools (Figma etc.) | ৳ 4,900 | ৳ 4,900 | ৳ 4,900 | ৳ 14,700 |
| Hardware Depreciation | ৳ 4,000 | ৳ 4,000 | ৳ 4,000 | ৳ 12,000 |
| Testing / Devices | ৳ 1,000 | ৳ 1,000 | ৳ 1,000 | ৳ 3,000 |
| Indirect Costs | ৳ 4,200 | ৳ 4,200 | ৳ 4,200 | ৳ 12,600 |
| ──── Monthly Total | ৳1,04,100 | ৳1,04,100 | ৳1,04,100 | ৳3,12,300 |
| Cumulative (Cost Baseline) | ৳1,04,100 | ৳2,08,200 | ৳3,12,300 | ৳3,12,300 |

Note: The even monthly distribution reflects fixed salaries. Variable sprint costs remain absorbed within overhead.

8. Earned Value Analysis (EVM) Framework

The following EVM parameters are defined for mid-project performance tracking (end of Month 1 snapshot).

| EVM Term | Formula | Planned Value (End of Month 1) |
| --- | --- | --- |
| Budget at Completion (BAC) | Total cost baseline | ৳ 3,12,300 |
| Planned Value (PV) | BAC × % work planned | ৳ 1,04,100 (33.3%) |
| Earned Value (EV) | BAC × % work completed | Measured at checkpoint |
| Actual Cost (AC) | Actual money spent | Tracked monthly |
| Cost Variance (CV) | EV − AC | +ve = under budget |
| Schedule Variance (SV) | EV − PV | +ve = ahead of schedule |
| Cost Performance Index (CPI) | EV ÷ AC | >1 = cost-efficient |
| Schedule Performance Index (SPI) | EV ÷ PV | >1 = ahead of schedule |
| Estimate at Completion (EAC) | BAC ÷ CPI | Revised forecast |
| Estimate to Complete (ETC) | EAC − AC | Remaining cost needed |
| Variance at Completion (VAC) | BAC − EAC | +ve = under; −ve = over |

9. Real-World vs. Academic Production Cost Comparison

This section benchmarks the Medicure academic project cost against a professionally contracted equivalent.

| Parameter | Academic Project (This Report) | Real-World Production Estimate |
| --- | --- | --- |
| Team Size | 2 Developers (Student/Junior rate) | 4–6 Developers (Professional rate) |
| Duration | 3 Months | 6–9 Months |
| Senior Dev Rate/Month | ৳ 60,000 | ৳ 1,20,000 – ৳ 1,80,000 |
| Junior Dev Rate/Month | ৳ 30,000 | ৳ 60,000 – ৳ 80,000 |
| Labor Cost | ৳ 2,70,000 | ৳ 15,00,000 – ৳ 40,00,000 |
| Software & Tools | ৳ 14,700 (OSS-based) | ৳ 1,50,000+ (Enterprise licenses) |
| Infrastructure/Hosting | ৳ 3,000 (local) | ৳ 50,000+ (Cloud: AWS/Azure) |
| QA & Security Testing | Included in dev hours | ৳ 3,00,000 – ৳ 5,00,000 |
| Total Budget | ৳ 3,59,157 | ৳ 20,00,000 – ৳ 50,00,000+ |

10. Key Assumptions & Constraints

1. Salary rates are based on the Dhaka, Bangladesh mid-market (2025–2026 reference).

2. Both developers work full-time (approximately 6 billable hours/working day, 22 days/month).

3. Development uses only open-source infrastructure (XAMPP, PHP, MySQL) — no cloud hosting costs incurred during development.

4. No physical office space is required; all work is remote/home-based (utilities absorbed in indirect costs).

5. The cost baseline is fixed at ৳3,12,300. Changes require a formal change request.

6. Contingency reserve (৳31,230) is controlled by the project lead and released only upon approved risk events.

7. Management reserve (৳15,627) is held by the project sponsor and not accessible without escalation.

8. All costs are denominated in BDT (Bangladeshi Taka). No foreign exchange exposure.

Medicure Project — Cost Analysis Report  |  CSE495 IT Project Management  |  East West University