MEDICURE

Digital Health & Pharmacy Management Platform

Final Project Report

| Prepared By | Saleh Kabir (Seendid) |
| --- | --- |
| Platform | Web Application – PHP / MySQL / XAMPP |
| Team | 2 Developers (1 Senior, 1 Junior) |
| Duration | 3 Months ¦ April – June 2026 |
| Repository | github.com/Seendid4evr/Medicature |

1. Project Description

Medicure is a comprehensive, full-stack digital health platform built to address the challenges faced by patients and caregivers in Bangladesh when managing medications. It combines medication scheduling, AI-powered symptom checking, an offline drug reference database of over 21,000 Bangladeshi medicines, and an integrated e-pharmacy purchasing system — all within a single, mobile-responsive web application built with PHP, MySQL, HTML/CSS/JavaScript, and XAMPP.

Core Features

Smart medication tracking with browser-based alarms

AI-powered symptom triage with OTC medicine suggestions and mandatory safety disclaimer

Searchable database of 21,000+ Bangladeshi brand medicines

Family member / dependent health management

E-pharmacy integration — Buy prescriptions from Arogga

Printable 7-day medication adherence reports

BMI and Ideal Weight health calculators

Admin dashboard: manage patients, send notifications, view full profiles

Password recovery, notification settings, profile management

Progressive Web App (PWA) support for mobile installation

2. Stakeholders

| # | Stakeholder | Role | Interest |
| --- | --- | --- | --- |
| 1 | Patients (Primary Users) | End-users | Track medications, reminders, drug info, buy medicines |
| 2 | Family Caregivers | Secondary users | Manage medications for dependents |
| 3 | System Administrator | Platform manager | Oversee users, send notifications |
| 4 | Pharmacies / Arogga | External partner | Receive purchase redirects |
| 5 | Healthcare Professionals | Indirect beneficiaries | Receive patient adherence reports |
| 6 | Developer / Project Owner | Builder & maintainer | Development, deployment, maintenance |
| 7 | University / Assessors | Evaluators | Review as academic submission |

3. Value Proposition

"Medicure gives every Bangladeshi patient a personal, intelligent, and connected health management system — for free."

| Problem | Medicure Solution |
| --- | --- |
| Patients forget medicines | Browser alarm fires at exact scheduled time |
| Don't know what medicine does | 21,000+ drug database with generics, side effects, indications |
| Managing family medicines | Dependent system: one account manages all family members |
| Refilling prescriptions | Buy Now button links directly to Arogga with medicine pre-searched |
| No medication history | 7-day adherence report, printable for doctors |
| Uncertain about symptoms | AI Triage suggests OTC medicines with mandatory safety disclaimer |
| Admin has no visibility | Full admin dashboard with patient details and history |

4. Work Breakdown Structure (WBS)

The project is decomposed using a Phase-Based WBS into 5 phases and 18 work packages across 3 months.

Figure 1: Medicure WBS – Phase-Based | 5 Phases | 18 Work Packages | 708 Total Hours

| WBS ID | Phase / Task | Assigned To | Hours | Month |
| --- | --- | --- | --- | --- |
| 1.1 | Requirements & Scope Analysis | Both Devs | 20 | Month 1 |
| 1.2 | Feasibility Study | Dev 1 (Senior) | 12 | Month 1 |
| 1.3 | Project Charter & Planning | Both Devs | 12 | Month 1 |
| 2.1 | UI/UX Wireframes & Mockups | Dev 2 (Junior) | 32 | Month 1 |
| 2.2 | Database Schema Design | Dev 1 (Senior) | 24 | Month 1 |
| 2.3 | System Architecture Planning | Dev 1 (Senior) | 16 | Month 1 |
| 3.1 | Backend – PHP, Auth, DB, APIs | Dev 1 (Senior) | 136 | Month 2 |
| 3.2 | Frontend – HTML/CSS/JS, Dashboard | Dev 2 (Junior) | 112 | Month 2 |
| 3.3 | Symptom Checker AI Module | Dev 1 (Senior) | 56 | Month 2 |
| 3.4 | Pharmacy & Medicines Module | Both Devs | 56 | Month 2 |
| 3.5 | Family Health Management Module | Both Devs | 40 | Month 2 |
| 3.6 | Reports & Health Calculators | Both Devs | 40 | Month 2 |
| 4.1 | Unit & Integration Testing | Dev 2 (Junior) | 36 | Month 3 |
| 4.2 | User Acceptance Testing (UAT) | Both Devs | 24 | Month 3 |
| 4.3 | Bug Fixing & QA Review | Both Devs | 32 | Month 3 |
| 5.1 | Server Setup & Deployment | Dev 1 (Senior) | 24 | Month 3 |
| 5.2 | Documentation & User Manual | Dev 2 (Junior) | 24 | Month 3 |
| 5.3 | Final Handover & Training | Both Devs | 12 | Month 3 |
| TOTAL | — | — | 708 hrs | 3 Months |

5. Cost Analysis

Team: 2 Developers (1 Senior @ ৳60,000/mo + 1 Junior @ ৳30,000/mo) over 3 months. Bangladesh market rates, April 2026.

5.1 Team & Labor Costs

| Role | Monthly Salary (BDT) | 3-Month Cost (BDT) | Working Hours/Month |
| --- | --- | --- | --- |
| Developer 1 – Senior / Full-Stack Lead | ৳ 60,000 | ৳ 1,80,000 | 176 hrs |
| Developer 2 – Junior / Frontend & QA | ৳ 30,000 | ৳ 90,000 | 176 hrs |
| TOTAL | ৳ 90,000 / month | ৳ 2,70,000 | 352 hrs / month |

5.2 Direct Costs Breakdown

| Category | Item | Total (BDT) |
| --- | --- | --- |
| Labor – Senior Developer | Full-stack dev (3 months @ ৳60K/mo) | ৳ 1,80,000 |
| Labor – Junior Developer | Frontend & QA (3 months @ ৳30K/mo) | ৳ 90,000 |
| Software – Design Tools | Figma Pro (3 months × ৳2,500/mo) | ৳ 7,500 |
| Software – AI Assist | GitHub Copilot × 2 devs (৳1,200/mo) | ৳ 7,200 |
| Hardware | Laptop depreciation × 2 devs (৳2,000/mo) | ৳ 12,000 |
| Infrastructure (Dev) | XAMPP, PHP, MySQL, Git | ৳ 0 |
| Testing | Device/browser testing allocation | ৳ 3,000 |
|  | DIRECT COST SUBTOTAL | ৳ 2,99,700 |

5.3 Indirect Costs

| Category | Item | 3-Month Total (BDT) |
| --- | --- | --- |
| Infrastructure | Internet – broadband 2 devs (৳700/mo each) | ৳ 4,200 |
| Infrastructure | Electricity / server allocation | ৳ 3,000 |
| Administrative | Project management & meeting overhead | ৳ 2,400 |
| Communication | Slack, cloud storage, email | ৳ 1,500 |
| Training | Online references & documentation | ৳ 1,500 |
|  | INDIRECT COST SUBTOTAL | ৳ 12,600 |

5.4 Cost Baseline & Total Budget

| Budget Component | Amount (BDT) | Notes |
| --- | --- | --- |
| A. Direct Costs | ৳ 2,99,700 | Labor, tools, hardware |
| B. Indirect Costs | ৳ 12,600 | Overhead & operational |
| ── COST BASELINE (A+B) | ৳ 3,12,300 | Performance reference |
| C. Contingency Reserve (10%) | ৳ 31,230 | Known risks buffer |
| ── CONTROL ACCOUNT BUDGET | ৳ 3,43,530 | With contingency |
| D. Management Reserve (5%) | ৳ 15,627 | Unknown risks – sponsor held |
| ══ TOTAL PROJECT BUDGET | ৳ 3,59,157 | Full authorization level |

5.5 Time-Phased Budget (Monthly Distribution)

| Cost Item | Month 1 – Apr 2026 | Month 2 – May 2026 | Month 3 – Jun 2026 | Total |
| --- | --- | --- | --- | --- |
| Senior Developer | ৳ 60,000 | ৳ 60,000 | ৳ 60,000 | ৳ 1,80,000 |
| Junior Developer | ৳ 30,000 | ৳ 30,000 | ৳ 30,000 | ৳ 90,000 |
| Software Tools | ৳ 4,900 | ৳ 4,900 | ৳ 4,900 | ৳ 14,700 |
| Hardware Depreciation | ৳ 4,000 | ৳ 4,000 | ৳ 4,000 | ৳ 12,000 |
| Testing & Devices | ৳ 1,000 | ৳ 1,000 | ৳ 1,000 | ৳ 3,000 |
| Indirect Costs | ৳ 4,200 | ৳ 4,200 | ৳ 4,200 | ৳ 12,600 |
| Monthly Total | ৳1,04,100 | ৳1,04,100 | ৳1,04,100 | ৳ 3,12,300 |
| Cumulative (Baseline) | ৳1,04,100 | ৳2,08,200 | ৳3,12,300 | ৳ 3,12,300 |

5.6 Real-World vs. Academic Cost Comparison

| Parameter | This Project (Academic) | Real-World Production |
| --- | --- | --- |
| Team Size | 2 Developers | 4–6 Developers (professional) |
| Duration | 3 Months | 6–9 Months |
| Senior Dev Rate | ৳ 60,000/month | ৳ 1,20,000–৳ 1,80,000/month |
| Junior Dev Rate | ৳ 30,000/month | ৳ 60,000–৳ 80,000/month |
| Hosting | XAMPP local (৳0) | AWS/DigitalOcean ৳8,000–৳15,000/mo |
| Medicine DB | Manually curated (৳0) | IMS Health API ৳22,000–৳55,000/mo |
| AI Engine | Knowledge-based (৳0) | OpenAI GPT-4o ৳3,300–৳8,800/mo |
| Total Budget | ৳ 3,59,157 | ৳ 20,00,000 – ৳ 50,00,000+ |

5.7 Earned Value Analysis (EVM) Framework

EVM parameters for performance tracking (end-of-Month 1 baseline):

| EVM Metric | Formula | End-of-Month-1 Value |
| --- | --- | --- |
| Budget at Completion (BAC) | Total cost baseline | ৳ 3,12,300 |
| Planned Value (PV) | BAC × % work planned | ৳ 1,04,100 (33.3%) |
| Cost Variance (CV) | EV − AC | +ve = under budget |
| Schedule Variance (SV) | EV − PV | +ve = ahead of schedule |
| Cost Performance Index (CPI) | EV ÷ AC | >1 = cost-efficient |
| Schedule Performance Index (SPI) | EV ÷ PV | >1 = on/ahead of schedule |
| Estimate at Completion (EAC) | BAC ÷ CPI | Revised forecast |
| Variance at Completion (VAC) | BAC − EAC | +ve = under; −ve = over budget |

6. SWOT Analysis

Strengths ✅

| # | Strength | Detail |
| --- | --- | --- |
| 1 | Bangladesh-specific | 21,000+ drug database curated for BD market — free |
| 2 | All-in-one platform | Tracking, AI triage, drug search, family, pharmacy, reports, admin |
| 3 | Zero cost for patients | Free to register and use |
| 4 | Works on any device | Responsive; installable as PWA without app store |
| 5 | Smart alarm system | Browser-native alarms fire in background |
| 6 | Admin control | Full admin panel for platform management |

Weaknesses ⚠️

| # | Weakness | Detail |
| --- | --- | --- |
| 1 | Local hosting only | Runs on XAMPP (localhost), not live server |
| 2 | No native mobile app | PWA-ready, but native Android/iOS would improve UX |
| 3 | Email requires SMTP config | Broadcast feature needs manual SMTP setup |
| 4 | No real payment gateway | Pharmacy links to Arogga but no in-app payment processing |

Opportunities 🚀

| # | Opportunity | Detail |
| --- | --- | --- |
| 1 | Growing digital health in BD | Perfect timing — BD healthcare digitalization expanding rapidly |
| 2 | Pharmacy partnerships | Arogga/Chaldal Health could be formal referral partners |
| 3 | Doctor portal expansion | Physician module to view patient reports directly |
| 4 | Government integration | Align with Shasthya Batayon (16789) eHealth initiatives |
| 5 | Multilingual support | Bangla (বাংলা) UI would dramatically increase user base |
| 6 | Cloud deployment | DigitalOcean/AWS deployment for nationwide access |

Threats ⚡

| # | Threat | Detail |
| --- | --- | --- |
| 1 | Competition | Praava Health, Ada, Babylon have bigger teams and budgets |
| 2 | Data privacy laws | Future BDRC regulations may require compliance updates |
| 3 | AI over-reliance | Patients may misuse AI Triage for self-medication |
| 4 | Internet dependency | Rural BD connectivity issues for Arogga links & email broadcast |
| 5 | Database staleness | 21,000+ medicines must be updated as drug market changes |

7. Conclusion

Medicure is a well-rounded, practical, and locally-relevant digital health solution. Built by a 2-developer team over 3 months at a total project budget of ৳3,59,157 BDT, it demonstrates strong command of full-stack web development, database design, UX principles, and real-world health technology challenges.

By leveraging 100% free and open-source tools (PHP, MySQL, XAMPP), the project saved an estimated ৳26,00,000+ per year compared to a fully commercial, enterprise-grade alternative. With further development — particularly live deployment, native mobile app development, and formal pharmacy partnerships — Medicure has genuine potential to become a meaningful healthcare tool for patients across Bangladesh.

Medicure — Final Project Report  |  CSE495 IT Project Management  |  East West University  |  April 2026